## Sheet1
# | Item | Estimation (hour) | Due date | Status
1 | Using docker-compose to start necessary services | 1 | 2020-02-06 | IN PROGRESS
2 | CRUD functions for Charge entity with Kotlin, Spring Boot, Spring Data JPA | 2 | 2020-02-06 | IN PROGRESS
3 | Using Flyway to initialize the CHARGE table | 2 | 2020-02-06 | IN PROGRESS
4 | Supporting paging, sorting | 2 | 2020-03-06 | OPEN
5 | Supporting multi-criteria search | 2 | 2020-03-06 | OPEN
6 | Supporting global exception handling | 2 | 2020-03-06 | OPEN
7 | Writing unit test with Junit, Mockito, memory db, Flyway | 4 | 2020-04-06 | OPEN
8 | Defining Avro schema | 2 | 2020-04-06 | IN PROGRESS
9 | Connecting Kafka to Schema Registry | 1 | 2020-04-06 | IN PROGRESS
10 | Listening to events which are sent after Charge records are updated | 2 | 2020-04-06 | OPEN
11 | Using Flyway to initialize the CHARGE_HISTORY table | 1 | 2020-04-06 | OPEN
12 | Using JWT with role based authentication | 2 | 2020-04-06 | OPEN
13 | Using Jasypt to encrypt sensitive configuration in property files | 1 | 2020-04-06 | OPEN
| Total | 24